## Sheet1
SEF Jira
Displaying 86 issues at 17/Sep/15 4:30 PM.
Issue Type | Key | Summary | Assignee | Reporter | Priority | Status | Resolution | Created | Updated | Due Date
Sub-task | ZERTWO-91 | ZERTWO-28 Write test cases | Yuet Yiu To | Yuet Yiu To | Must Have | Open | Unresolved | 2015-09-14 18:01 | 2015-09-14 18:01 | 2015-09-08
Sub-task | ZERTWO-90 | ZERTWO-28 Verify story is complete (acceptance test) | Yuet Yiu To | Yuet Yiu To | Must Have | Open | Unresolved | 2015-09-14 18:01 | 2015-09-14 18:01 | 2015-09-08
Sub-task | ZERTWO-89 | ZERTWO-1 Verify story is complete (acceptance test) | Unassigned | Yuet Yiu To | Must Have | Open | Unresolved | 2015-09-14 17:56 | 2015-09-14 17:59 | 2015-09-08
Sub-task | ZERTWO-88 | ZERTWO-1 Write test cases | Unassigned | Yuet Yiu To | Must Have | Open | Unresolved | 2015-09-14 17:56 | 2015-09-14 17:59 | 2015-09-08
Sub-task | ZERTWO-87 | ZERTWO-6 Create tables to store help request in database | Amanda Jarvinen | Yuet Yiu To | Must Have | Resolved | Done | 2015-09-14 17:28 | 2015-09-17 15:51 | 2015-09-22
Sub-task | ZERTWO-86 | ZERTWO-6 Write code to insert help request details in database | Amanda Jarvinen | Yuet Yiu To | Must Have | Open | Unresolved | 2015-09-14 17:28 | 2015-09-14 19:59 | 2015-09-22
Sub-task | ZERTWO-85 | ZERTWO-6 Write code to retrieve all of client’s help request id’s and names from database | Amanda Jarvinen | Yuet Yiu To | Must Have | Open | Unresolved | 2015-09-14 17:28 | 2015-09-14 19:59 | 2015-09-22
Sub-task | ZERTWO-84 | ZERTWO-6 Write code to retrieve help request details from database | Amanda Jarvinen | Yuet Yiu To | Must Have | Open | Unresolved | 2015-09-14 17:28 | 2015-09-14 19:58 | 2015-09-22
Sub-task | ZERTWO-83 | ZERTWO-6 Create help request form | Samuel Burns | Yuet Yiu To | Must Have | Open | Unresolved | 2015-09-14 17:28 | 2015-09-17 11:03 | 2015-09-22
Sub-task | ZERTWO-82 | ZERTWO-6 Create page to view all of client’s help requests | Samuel Burns | Yuet Yiu To | Must Have | Open | Unresolved | 2015-09-14 17:27 | 2015-09-17 11:03 | 2015-09-22
Sub-task | ZERTWO-81 | ZERTWO-6 Create page to view help request details | Samuel Burns | Yuet Yiu To | Must Have | Open | Unresolved | 2015-09-14 17:27 | 2015-09-17 11:03 | 2015-09-22
Sub-task | ZERTWO-80 | ZERTWO-6 Verify story is complete (acceptance test) | Yuet Yiu To | Yuet Yiu To | Must Have | In Progress | Unresolved | 2015-09-14 17:27 | 2015-09-14 17:47 | 2015-09-22
Sub-task | ZERTWO-79 | ZERTWO-6 Write test cases | Yuet Yiu To | Yuet Yiu To | Must Have | In Progress | Unresolved | 2015-09-14 17:27 | 2015-09-14 17:47 | 2015-09-22
Sub-task | ZERTWO-73 | ZERTWO-2 Create edit details form | Unassigned | Yuet Yiu To | Must Have | Open | Unresolved | 2015-09-14 17:16 | 2015-09-14 17:16 | 2015-09-22
Sub-task | ZERTWO-72 | ZERTWO-2 Write code to query email, first name, last name and hash in database | Unassigned | Yuet Yiu To | Must Have | Open | Unresolved | 2015-09-14 17:16 | 2015-09-14 17:16 | 2015-09-22
Sub-task | ZERTWO-71 | ZERTWO-2 Create form requesting email. first name and last name | Unassigned | Yuet Yiu To | Must Have | Open | Unresolved | 2015-09-14 17:15 | 2015-09-14 17:15 | 2015-09-22
Sub-task | ZERTWO-70 | ZERTWO-2 Verify story complete (acceptance test) | Unassigned | Yuet Yiu To | Must Have | Open | Unresolved | 2015-09-14 17:14 | 2015-09-14 17:17 | 2015-09-22
Sub-task | ZERTWO-69 | ZERTWO-2 Write test cases | Unassigned | Yuet Yiu To | Must Have | Open | Unresolved | 2015-09-14 17:13 | 2015-09-14 17:13 | 2015-09-22
Sub-task | ZERTWO-68 | ZERTWO-4 Write code to delete help request | Leandro Veloso Rodrigues | Yuet Yiu To | Must Have | In Progress | Unresolved | 2015-09-14 17:11 | 2015-09-17 10:56 | 2015-09-22
Sub-task | ZERTWO-67 | ZERTWO-4 Write code to update help request details in datavase | Amanda Jarvinen | Yuet Yiu To | Must Have | Open | Unresolved | 2015-09-14 17:11 | 2015-09-17 11:01 | 2015-09-22
Sub-task | ZERTWO-66 | ZERTWO-4 Write code to retrieve help request details from database | Amanda Jarvinen | Yuet Yiu To | Must Have | Open | Unresolved | 2015-09-14 17:10 | 2015-09-17 11:00 | 2015-09-22
Sub-task | ZERTWO-65 | ZERTWO-4 Create page to edit client help request | Leandro Veloso Rodrigues | Yuet Yiu To | Must Have | In Progress | Unresolved | 2015-09-14 17:08 | 2015-09-17 10:56 | 2015-09-22
Sub-task | ZERTWO-64 | ZERTWO-4 Add delete function to view help request page | Leandro Veloso Rodrigues | Yuet Yiu To | Must Have | In Progress | Unresolved | 2015-09-14 17:08 | 2015-09-17 10:56 | 2015-09-22
Sub-task | ZERTWO-63 | ZERTWO-4 Verify story is complete (Acceptance test) | Samuel Burns | Yuet Yiu To | Must Have | Open | Unresolved | 2015-09-14 17:05 | 2015-09-17 10:57 | 2015-09-22
Sub-task | ZERTWO-62 | ZERTWO-4 Write test cases | Samuel Burns | Yuet Yiu To | Must Have | Open | Unresolved | 2015-09-14 17:04 | 2015-09-17 10:57 | 2015-09-22
Sub-task | ZERTWO-61 | ZERTWO-55 Verify story complete (acceptance test) | Chen Pin Leong | Yuet Yiu To | Must Have | Open | Unresolved | 2015-09-14 16:54 | 2015-09-17 10:58 | 2015-09-22
Sub-task | ZERTWO-60 | ZERTWO-55 Write code to retrieve user details from database | Yuet Yiu To | Yuet Yiu To | Must Have | Resolved | Fixed | 2015-09-14 16:53 | 2015-09-15 14:12 | 2015-09-22
Sub-task | ZERTWO-59 | ZERTWO-55 Write test cases | Chen Pin Leong | Yuet Yiu To | Must Have | Open | Unresolved | 2015-09-14 16:52 | 2015-09-17 10:58 | 2015-09-22
Sub-task | ZERTWO-58 | ZERTWO-55 Write code to update user details in database | Yuet Yiu To | Yuet Yiu To | Must Have | In Progress | Unresolved | 2015-09-14 16:52 | 2015-09-14 17:45 | 2015-09-22
Sub-task | ZERTWO-57 | ZERTWO-55 Create edit details form | Yuet Yiu To | Yuet Yiu To | Must Have | In Progress | Unresolved | 2015-09-14 16:50 | 2015-09-14 17:45 | 2015-09-22
Sub-task | ZERTWO-56 | ZERTWO-55 Create account summary page | Yuet Yiu To | Chen Pin Leong | Must Have | Resolved | Fixed | 2015-09-14 16:49 | 2015-09-15 14:12 | 2015-09-22
Story | ZERTWO-55 | Manage account [GENERAL USER] | Unassigned | Amanda Jarvinen | Must Have | Open | Unresolved | 2015-09-14 16:17 | 2015-09-14 16:22 | 2015-09-22
Sub-task | ZERTWO-54 | ZERTWO-28 Configure SMTP | Samuel Burns | Samuel Burns | Trivial | Resolved | Fixed | 2015-08-25 21:23 | 2015-09-14 14:29
Sub-task | ZERTWO-53 | ZERTWO-28 Integrate appropriate php mailing library | Samuel Burns | Samuel Burns | Trivial | Resolved | Done | 2015-08-25 21:23 | 2015-09-14 14:35
Sub-task | ZERTWO-52 | ZERTWO-28 Create form to send message to volunteers | Samuel Burns | Samuel Burns | Trivial | Resolved | Done | 2015-08-25 21:22 | 2015-09-14 14:28
Sub-task | ZERTWO-51 | ZERTWO-49 Choose Appropriate layout for service tools | Chen Pin Leong | Samuel Burns | Trivial | Resolved | Fixed | 2015-08-25 21:00 | 2015-09-14 14:42
Sub-task | ZERTWO-50 | ZERTWO-49 Choose Appropriate colour scheme | Chen Pin Leong | Samuel Burns | Trivial | Resolved | Fixed | 2015-08-25 21:00 | 2015-09-14 14:41
Story | ZERTWO-49 | Service design [GENERAL USER] | Chen Pin Leong | Samuel Burns | Critical | Resolved | Done | 2015-08-25 20:47 | 2015-09-07 16:27
Sub-task | ZERTWO-48 | ZERTWO-4 Job request information can be updated in database | Leandro Veloso Rodrigues | Samuel Burns | Trivial | In Progress | Unresolved | 2015-08-25 20:22 | 2015-09-17 10:56
Sub-task | ZERTWO-47 | ZERTWO-4 Job requests can be deleted from database | Leandro Veloso Rodrigues | Samuel Burns | Trivial | In Progress | Unresolved | 2015-08-25 20:22 | 2015-09-17 10:56
Sub-task | ZERTWO-46 | ZERTWO-4 Create page displaying all of the clients current job request | Leandro Veloso Rodrigues | Samuel Burns | Trivial | In Progress | Unresolved | 2015-08-25 20:21 | 2015-09-17 10:56
Sub-task | ZERTWO-45 | ZERTWO-28 Create page with contact information (email, phone) | Samuel Burns | Samuel Burns | Trivial | Resolved | Done | 2015-08-25 19:23 | 2015-09-14 14:28
Sub-task | ZERTWO-44 | ZERTWO-1 Create database table to store user account information | Amanda Jarvinen | Samuel Burns | Trivial | Resolved | Done | 2015-08-25 19:04 | 2015-08-31 23:54
Sub-task | ZERTWO-43 | ZERTWO-6 Send notification to volunteer accounts | Samuel Burns | Samuel Burns | Trivial | Open | Unresolved | 2015-08-25 19:02 | 2015-09-17 11:03
Sub-task | ZERTWO-42 | ZERTWO-6 Create job request table in database | Samuel Burns | Samuel Burns | Trivial | Open | Unresolved | 2015-08-25 18:59 | 2015-09-17 11:02
Sub-task | ZERTWO-41 | ZERTWO-6 Store job request in request table | Samuel Burns | Samuel Burns | Trivial | Open | Unresolved | 2015-08-25 18:58 | 2015-09-17 11:02
Sub-task | ZERTWO-40 | ZERTWO-6 Implement Javascript code to perform field validation | Samuel Burns | Samuel Burns | Trivial | Open | Unresolved | 2015-08-25 18:58 | 2015-09-17 11:02
Sub-task | ZERTWO-39 | ZERTWO-6 Create the necessary fields for a job request to be made | Samuel Burns | Samuel Burns | Trivial | Open | Unresolved | 2015-08-25 18:58 | 2015-09-17 11:02
Sub-task | ZERTWO-38 | ZERTWO-2 Store updated password in database | Samuel Burns | Samuel Burns | Trivial | Open | Unresolved | 2015-08-25 18:50 | 2015-08-31 14:53
Sub-task | ZERTWO-37 | ZERTWO-2 Implement Javascript for field validation | Samuel Burns | Samuel Burns | Trivial | In Progress | Unresolved | 2015-08-25 18:50 | 2015-09-08 12:48
Sub-task | ZERTWO-36 | ZERTWO-2 Create form to change password | Samuel Burns | Samuel Burns | Trivial | In Progress | Unresolved | 2015-08-25 18:49 | 2015-09-08 12:48
Sub-task | ZERTWO-35 | ZERTWO-2 Prompt user with secret question | Samuel Burns | Samuel Burns | Trivial | Open | Unresolved | 2015-08-25 18:48 | 2015-08-31 14:57
Sub-task | ZERTWO-34 | ZERTWO-1 Have site maintain state, so users can make use of member only functionality | Yuet Yiu To | Samuel Burns | Trivial | Resolved | Fixed | 2015-08-25 18:46 | 2015-09-14 14:27
Sub-task | ZERTWO-33 | ZERTWO-1 Save user details in account database table | Amanda Jarvinen | Samuel Burns | Trivial | Resolved | Done | 2015-08-25 18:41 | 2015-09-14 14:27
Sub-task | ZERTWO-32 | ZERTWO-1 Implement Javascript code to perform field validation | Leandro Veloso Rodrigues | Samuel Burns | Trivial | Resolved | Fixed | 2015-08-25 18:41 | 2015-09-13 00:27
Sub-task | ZERTWO-31 | ZERTWO-1 Create necessary fields | Amanda Jarvinen | Samuel Burns | Trivial | Closed | Done | 2015-08-25 18:40 | 2015-09-14 14:27
Sub-task | ZERTWO-30 | ZERTWO-27 Create 'about' page | Chen Pin Leong | Samuel Burns | Trivial | Resolved | Fixed | 2015-08-25 18:39 | 2015-09-14 14:40
Sub-task | ZERTWO-29 | ZERTWO-27 Create service description | Amanda Jarvinen | Samuel Burns | Must Have | Resolved | Done | 2015-08-25 18:38 | 2015-09-13 22:11
Story | ZERTWO-28 | Contact here2help [VISITOR] | Samuel Burns | Amanda Jarvinen | Must Have | Resolved | Done | 2015-08-20 19:26 | 2015-09-14 14:38
Story | ZERTWO-27 | About here2help [VISITOR] | Samuel Burns | Amanda Jarvinen | Must Have | Resolved | Done | 2015-08-20 19:24 | 2015-09-14 14:41
Story | ZERTWO-26 | Search Service Providers [VOLUNTEER] | Unassigned | Amanda Jarvinen | Could Have | Open | Unresolved | 2015-08-20 19:03 | 2015-08-25 19:26
Story | ZERTWO-25 | Store Service Provider Details [VOLUNTEER] | Unassigned | Amanda Jarvinen | Could Have | Open | Unresolved | 2015-08-20 18:59 | 2015-08-25 19:18
Story | ZERTWO-24 | Advertising [SERVICE PROVIDER] | Unassigned | Leandro Veloso Rodrigues | Should Have | Open | Unresolved | 2015-08-15 20:07 | 2015-08-25 19:18
Story | ZERTWO-23 | Service Information [SERVICE PROVIDER] | Unassigned | Leandro Veloso Rodrigues | Should Have | Open | Unresolved | 2015-08-15 20:04 | 2015-08-25 22:09
Story | ZERTWO-22 | Set Availability [VOLUNTEER] | Unassigned | Leandro Veloso Rodrigues | Could Have | Open | Unresolved | 2015-08-15 20:01 | 2015-08-25 19:25
Story | ZERTWO-21 | Create Roster [VOLUNTEER] | Unassigned | Leandro Veloso Rodrigues | Could Have | Open | Unresolved | 2015-08-15 19:57 | 2015-08-25 19:25
Story | ZERTWO-20 | View Roster [VOLUNTEER] | Unassigned | Leandro Veloso Rodrigues | Must Have | Open | Unresolved | 2015-08-15 19:43 | 2015-08-25 19:25
Story | ZERTWO-19 | Recover Password [SERVICE PROVIDER] | Unassigned | Leandro Veloso Rodrigues | Must Have | Closed | Won't Fix | 2015-08-15 19:37 | 2015-08-17 14:47
Story | ZERTWO-18 | Create and manage account [SERVICE PROVIDER] | Unassigned | Leandro Veloso Rodrigues | Must Have | Closed | Won't Fix | 2015-08-15 19:35 | 2015-08-17 14:47
Story | ZERTWO-17 | Create Help Request [VOLUNTEER] | Unassigned | Amanda Jarvinen | Could Have | Open | Unresolved | 2015-08-15 19:02 | 2015-09-14 16:59
Story | ZERTWO-16 | Assign Requests [VOLUNTEER] | Unassigned | Amanda Jarvinen | Should Have | Open | Unresolved | 2015-08-15 18:55 | 2015-09-14 16:59
Story | ZERTWO-15 | Booking [CLIENT] | Unassigned | Amanda Jarvinen | Must Have | Open | Unresolved | 2015-08-15 18:41 | 2015-09-14 16:59
Story | ZERTWO-14 | Volunteer Feedback [CLIENT] | Unassigned | Amanda Jarvinen | Could Have | Open | Unresolved | 2015-08-15 18:34 | 2015-08-25 19:26
Story | ZERTWO-13 | Record of Quotes [VOLUNTEER] | Unassigned | Amanda Jarvinen | Should Have | Open | Unresolved | 2015-08-15 18:20 | 2015-09-14 16:59
Story | ZERTWO-12 | Request Approval [VOLUNTEER] | Unassigned | Amanda Jarvinen | Must Have | Open | Unresolved | 2015-08-15 18:14 | 2015-09-14 16:59
Story | ZERTWO-11 | Service Provider Feedback [VOLUNTEER] | Unassigned | Amanda Jarvinen | Could Have | Open | Unresolved | 2015-08-15 17:51 | 2015-08-25 19:26
Story | ZERTWO-10 | Service Provider Feedback [CLIENT] | Unassigned | Amanda Jarvinen | Should Have | Open | Unresolved | 2015-08-15 17:50 | 2015-08-25 19:24
Story | ZERTWO-9 | Create and manage account [VOLUNTEER] | Unassigned | Amanda Jarvinen | Must Have | Closed | Won't Fix | 2015-08-15 17:24 | 2015-08-20 16:20
Story | ZERTWO-8 | Recover Password [VOLUNTEER] | Unassigned | Amanda Jarvinen | Must Have | Closed | Won't Fix | 2015-08-15 17:21 | 2015-08-17 14:45
Story | ZERTWO-7 | Contact Client [VOLUNTEER] | Unassigned | Amanda Jarvinen | Should Have | Open | Unresolved | 2015-08-15 17:15 | 2015-08-25 19:19
Story | ZERTWO-6 | Create Request [CLIENT] | Unassigned | Amanda Jarvinen | Must Have | Open | Unresolved | 2015-08-15 16:50 | 2015-09-13 22:12
Story | ZERTWO-5 | Track Request [CLIENT] | Unassigned | Amanda Jarvinen | Should Have | Open | Unresolved | 2015-08-15 16:36 | 2015-09-14 16:59
Story | ZERTWO-4 | Manage Request [CLIENT] | Unassigned | Amanda Jarvinen | Must Have | Reopened | Unresolved | 2015-08-11 15:42 | 2015-09-13 22:12
Story | ZERTWO-3 | Create Help Request [CLIENT] | Unassigned | Amanda Jarvinen | Must Have | Closed | Won't Fix | 2015-08-11 15:35 | 2015-08-17 18:52
Story | ZERTWO-2 | Recover Password [GENERAL USER] | Samuel Burns | Amanda Jarvinen | Must Have | Open | Unresolved | 2015-08-11 15:31 | 2015-09-14 17:53
Story | ZERTWO-1 | Create account [GENERAL USER] | Unassigned | Amanda Jarvinen | Must Have | Resolved | Fixed | 2015-08-11 15:21 | 2015-09-14 17:14
Generated at Thu Sep 17 16:30:37 EST 2015 by Yuet Yiu To using JIRA 6.2.7#6265-sha1:91604a8de81892a3e362e0afee505432f29579b0.